## tradesman_booking_features_esti
Category | Subcategory | Feature | Dependencies | Priority | Effort (Hours) | Impact | Compliance Note | Integration Options
User Experience | Booking Flow | Online booking form with fixed + customisable service options |  | Must-Have | 20 | High
User Experience | Booking Flow | Option for clients to upload photos when booking |  | Must-Have | 8 | High | Consent required for storing photos
User Experience | Booking Flow | Ability to split a job into multiple bookings |  | Must-Have | 4 | High
User Experience | Booking Flow | Parallel booking support (e.g., consultation during long job) |  | Must-Have | 12 | High
User Experience | Loyalty & Referrals | View loyalty points and referral rewards in client portal |  | Performance Driver | 12 | Medium |  | Custom rewards engine or third-party loyalty API
User Experience | Notifications | Automated booking confirmations and reminders |  | Must-Have | 8 | High
User Experience | Notifications | Cancellation and reschedule options for clients |  | Delighter | 4 | Low
User Experience | Messaging | Two-way client messaging (reply via SMS/email/portal) |  | Delighter | 16 | Low |  | Twilio / SendGrid / WhatsApp Business API
User Experience | Messaging | Receive auto-updates (on the way, arrived, delayed, completed) |  | Delighter | 12 | Low
User Experience | Privacy | Right to opt out of marketing but still receive operational updates |  | Performance Driver | 12 | Medium
Admin Experience | Booking Management | Admin dashboard for bookings, jobs, cancellations |  | Must-Have | 4 | High
Admin Experience | Booking Management | Team scheduling for up to 5 employees |  | Delighter | 4 | Low
Admin Experience | Booking Management | Add buffer time before/after bookings (travel/setup/admin) |  | Must-Have | 16 | High
Admin Experience | Job Completion | Completion form with before/after photos, comments, job status |  | Delighter | 12 | Low | Consent required for storing photos
Admin Experience | Messaging | Predefined quick client messages (On the way, Arrived, Delayed) |  | Must-Have | 12 | High | Messaging data retention policy applies | Twilio / SendGrid / WhatsApp Business API
Admin Experience | Messaging | Custom client messaging option |  | Delighter | 6 | Low
Admin Experience | Messaging | Automatic triggers for client messages based on booking status |  | Must-Have | 20 | High | Messaging data retention policy applies | Twilio / SendGrid / WhatsApp Business API
Admin Experience | Messaging | Two-way messaging hub with conversation history per booking |  | Must-Have | 16 | High
Admin Experience | Messaging | Multi-channel messaging (SMS, email, WhatsApp if integrated) |  | Delighter | 16 | Low |  | Twilio / SendGrid / WhatsApp Business API
Admin Experience | Messaging | Click-to-send updates via approved channels (SMS/email/etc.) |  | Delighter | 16 | Low |  | Twilio / SendGrid / WhatsApp Business API
Admin Experience | Quotes & Invoices | Convert booking into quote with one click |  | Must-Have | 8 | High |  | Xero / QuickBooks integration
Admin Experience | Quotes & Invoices | Loyalty/referral rewards auto-applied in quotes and invoices |  | Must-Have | 16 | High |  | Xero / QuickBooks integration, Custom rewards engine or third-party loyalty API
Admin Experience | Quotes & Invoices | Invoice flow with rewards displayed as line items |  | Must-Have | 4 | High |  | Xero / QuickBooks integration
Admin Experience | Calendar & Availability | Two-way sync with Google/Outlook/Apple Calendar |  | Must-Have | 6 | High |  | Google Calendar API / Microsoft Outlook API
Admin Experience | Calendar & Availability | Calendar conflict resolution rules |  | Must-Have | 4 | High |  | Google Calendar API / Microsoft Outlook API
Admin Experience | Calendar & Availability | Event listeners update booking DB from external calendars |  | Must-Have | 16 | High |  | Google Calendar API / Microsoft Outlook API
Admin Experience | CRM Integration | CRM integration (Zoho, HubSpot free tiers) |  | Delighter | 8 | Low |  | Zoho CRM / HubSpot CRM
Admin Experience | CRM Integration | Customer profiles with booking history, loyalty, referrals, messages |  | Must-Have | 12 | High | Messaging data retention policy applies | Twilio / SendGrid / WhatsApp Business API, Custom rewards engine or third-party loyalty API
Admin Experience | CRM Integration | Lead â†’ booking â†’ job â†’ payment pipeline in CRM |  | Must-Have | 4 | High |  | Zoho CRM / HubSpot CRM
Admin Experience | Marketing | Marketing automation for loyalty/referral campaigns |  | Performance Driver | 20 | Medium |  | Custom rewards engine or third-party loyalty API
Admin Experience | Loyalty & Referrals | Fraud prevention for loyalty/referrals |  | Performance Driver | 8 | Medium |  | Custom rewards engine or third-party loyalty API
Admin Experience | Loyalty & Referrals | Analytics for rewards and referrals |  | Performance Driver | 6 | Medium |  | Custom rewards engine or third-party loyalty API
Security | Data Protection | Encrypted booking and payment data |  | Must-Have | 6 | High
Security | Integration Security | Secure APIs for calendar and CRM integrations |  | Must-Have | 6 | High |  | Google Calendar API / Microsoft Outlook API, Zoho CRM / HubSpot CRM
Security | Integration Security | OAuth authentication for external calendars |  | Must-Have | 6 | High |  | Google Calendar API / Microsoft Outlook API
Security | Messaging Security | End-to-end encryption for two-way messaging |  | Delighter | 6 | Low
Security | Loyalty Security | Fraud detection for loyalty and referrals |  | Performance Driver | 6 | Medium |  | Custom rewards engine or third-party loyalty API
Security | Data Protection | Access control for job photos and client communication logs |  | Delighter | 16 | Low | Consent required for storing photos
Security | Audit | Audit trail for bookings, rewards, and messaging |  | Must-Have | 8 | High
GDPR & UK Act | Consent | Explicit opt-in for loyalty and referrals |  | Performance Driver | 6 | Medium | Requires GDPR compliance | Custom rewards engine or third-party loyalty API
GDPR & UK Act | Consent | Consent required for storing job completion photos |  | Delighter | 20 | Low | Requires GDPR compliance
GDPR & UK Act | Transparency | Privacy notice covering bookings, photos, and messages |  | Must-Have | 20 | High | Requires GDPR compliance | Twilio / SendGrid / WhatsApp Business API
GDPR & UK Act | Data Rights | Right to export or delete booking, loyalty, referral, and messaging history |  | Must-Have | 12 | High | Requires GDPR compliance | Custom rewards engine or third-party loyalty API
GDPR & UK Act | Calendar Privacy | Option to store personal calendar events as 'busy' only |  | Must-Have | 16 | High | Requires GDPR compliance | Google Calendar API / Microsoft Outlook API
GDPR & UK Act | Opt-out | Clear opt-out options for marketing communications |  | Performance Driver | 12 | Medium | Requires GDPR compliance
GDPR & UK Act | Retention | Data retention policy for client messages |  | Must-Have | 8 | High | Requires GDPR compliance | Twilio / SendGrid / WhatsApp Business API